## Login_testcases
Project Name | Zero bank | [8 empty] | Version | -
Processor+A:SB7A:M | [9 empty] | OS | Windows
RAM | - | [8 empty] | Browser | -
Module Name | login page
Reviewed By | Vaishali sonanis | [8 empty] | Date Reviewed on: | 2025-08-06
SR. NO. | TYPE OF TESTING | TEST CASES NO. | TEST CASE NAME | OBJECTIVE | PRE-REQUISITE | STEPS TO BE FOLLOWED | TEST DATA | EXPECTED OUTPUT | ACTUAL OUTPUT | PASSED / FAILED | BUG ID NO. | BUG ROOT CAUSE | WORK ITEM ASSOCIATED | MAJOR / MINOR BUG | IF MAJOR THEN TYPE | TESTED ON | TESTED BY | REMARKS
1 | functional testing | TC‑001 | TC_ZB_login_valid | Valid login | login page should be open in default browser | Enter valid username and password | username password | Successfully login and navigate to home page | showing error message "This site can’t provide a secure connection" | Fail
2 | functional testing | TC‑002 | TC_ZB_login_user_invalid | Invalid username | login page should be open in default browser | Enter invalid username + valid password; attempt login. | hgdjdgd, password | Display an error message; remain on login page. | display error message "Login and/or password invalid" | Passed
3 | functional testing | TC‑003 | TC_ZB_login_pass_invalid | Invalid password | login page should be open in default browser | Enter valid username + wrong password; attempt login. | username,hfdkjFKDJ | Display an error message; remain on login page. | display error message "Login and/or password invalid" | Passed
4 | functional testing | TC‑004 | TC_ZB_login_both_invalid | Both fields empty | login page should be open in default browser | Leave both username & password blank; click Login. | keep blank | Display validation messages for required fields. | display error message "Login and/or password invalid" | Passed
5 | functional testing | TC‑005 | TC_ZB_login_both_invalid | Both fields invalid | login page should be open in default browser | add both invalid username and password | hadkjf,gfdgdu 6747476,64343 #@%,$%@^$ | Display validation messages for required fields. | display error message "Login and/or password invalid" | Passed
6 | functional testing | TC‑006 | TC_ZB_login/logout | Session persistence after logout | login page should be open in default browser | Login, then log out and click browser back/reset tab. |  | logout and stay on home page without login | logout and stay on home page without login | Passed
7 | functional testing | TC‑007 | TC_ZB_checkbox | "Keep me signed in" functionality | login page should be open in default browser | Check "Keep me signed in", then close and reopen browser. |  | User stays logged in (if intended), or session is cleared. | yes able click and change selected and unselected | Passed
8 | functional testing | TC‑008 | TC_ZB_login_?Icon | Default credentials present | login page should be open in default browser | Inspect login hint (e.g., via the “?” icon). |  | Hint matches expected default credentials. | yes showing default username and password | Passed
9 | functional testing | TC‑009 | TC_ZB_login_forgotpassword | check forgot password link navigate to next page | login page should be open in default browser | open login page and click on forgot password link |  | forgot password link navigate to next relavant page | navigate to next page | Passed

## defect report
ØDefect identifier | Def_003
ØDefect summary | when hovering on the links in the nav bar only some links will dispaly a popup like message showing some extra information related to it .whereas to maintain unity in the website it fails.
ØTest Id | TC‑008
ØTest case name | TC_TB_navlinks_hover
ØModule name | Tira nav bar hovering
Øreproducible
Øseverity | medium
Øpriority | low
ØRaised by | Thotakuri Sai Kiran(Tester name)
ØAssigned to | Reeva Shah(TL name)
ØDate of assignment | 2025-08-08
Østatus | open
ØSnap shots
ØFixed by | Shiva Upadhyay(Developer name
ØDate of fixing=
ØApprovals=manager name | Nisha mandot(Manager name)
ØDefect identifier | Def_002
ØDefect summary | while hovering on the person icon in the nav bar as all the shapes in the website are four corners rounded but the card displayed after hovering doesnot contain rounded borders.
ØTest Id | TC‑005
ØTest case name | TC_TB_hoveronpersonicon
ØModule name | Tira
Øreproducible
Øseverity | low
Øpriority | low
ØRaised by | Thotakuri Sai Kiran(Tester name)
ØAssigned to | Reeva Shah(TL name)
ØDate of assignment | 2025-08-08
Østatus | open
ØSnap shots
ØFixed by | Shiva Upadhyay(Developer name
ØDate of fixing=
ØApprovals=manager name | Nisha mandot(Manager name)
ØDefect identifier | Def001
ØDefect summary | while we are providing an email for newsletters it is displaying a pop and there is no particular email confirmation to the valid email user such that he is subscribed to the newsletter.
ØTest Id | TC‑004
ØTest case name | TC_TB_subscribeemail
ØModule name | Tira
Øreproducible
Øseverity | low
Øpriority | low
ØRaised by | Thotakuri Sai Kiran(Tester name)
ØAssigned to | Reeva Shah(TL name)
ØDate of assignment | 2025-08-08
Østatus | open
ØSnap shots
ØFixed by | Shiva Upadhyay(Developer name
ØDate of fixing=
ØApprovals=manager name | Nisha mandot(Manager name)
ØDefect identifier | Def_004
ØDefect summary | while scrolling the products with the filter there is an issue with the scroll down.
ØTest Id | TC‑009
ØTest case name | TC_TB_scrolling_products
ØModule name | Tira
Øreproducible
Øseverity | low
Øpriority | low
ØRaised by | Thotakuri Sai Kiran(Tester name)
ØAssigned to | Reeva Shah(TL name)
ØDate of assignment | 2025-08-08
Østatus | open
ØSnap shots
ØFixed by | Shiva Upadhyay(Developer name
ØDate of fixing=
ØApprovals=manager name | Nisha mandot(Manager name)

## testAnalysis_report
Section | Details
Project Name | Zerobank
Module Name | login
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | Vaishali sonanis
Date | 2025-08-07
1. Test Summary
Metric | Count
Total Test Cases | 9
Executed Test Cases | 9
Passed Test Cases | 8
Failed Test Cases | 1
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | No
Manual Test Cases | 9
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 8 | 88.88%
Failed | 1 | 11%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 1
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 0
Low Severity Defects | 1
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 9 out of 9 covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
after login it will show "This site can’t provide a secure connection" but user is able to logedin
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
username and password easily available | Medium | Open | hide username and password
after login it will show this "This site can’t provide a secure connection" so this create confusion | Medium | Open | redirect to Home page
7. Recommendations
hide username and password
redirect to Home page